## NEW RACI FORMAT
| Tony Wineinger | George Kafkes | Mike Reckley | Mark Beranek | Jim Holder | Charlene Cooley | Tuanna Freeman | Joyjit Ghosh | Kabenna Kirkwood | Masoud Majidi | Steve Pichon | Suman Beereddy | Mohammed Fayaz | Gurpreet Singh | Dan Foelker | Matt Michel | Ron Garske | Connie Bandt | Agency LCON
Deliverable or Task | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
| AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
AT&T Core Data Center Service Implementation - Definition (Section 3.4) |  |  | I | C | I |  |  |  | R | I | A
Network - WAN, PoE, QoS, VoIP readiness on Agency Site - Definition (Section 4) | [13 empty] | R | R | I | I | I | R
Pre-Migration Prep | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
Agency Kickoff - Agency provides pre-popluated workbook. (should provide Active Directory & BTN info) | [5 empty] | I | [7 empty] | C | C | C | C | C | R
AT&T Account Team and DET interlock with agency to review requirements & completed workbook | A | C |  |  |  | I | I | I | I | I | I | I | I | C | C | C | C | C | R
DET initates initial network & infrastructure assesment | [5 empty] | I | I | I | I | I | I | I | I | R | R | R | I | I | R
DET Provides Reqested firewall rules (subnets, gateways, etc) to AT&T UC NOC Team | I | I |  |  | I | [8 empty] | R | C | I | I | I | I
UC NOC team implements firewall rules - is there testing? | I | I |  |  | I | A |  | R | [5 empty] | I | I
AT&T NI requests AT&T UC team to create a Change Order | I | R | A |  | I | I |  |  |  | I |  |  |  | I | I | I | I | I | C
AT&T UC Team Creates a CO and submits to NI | I | I | I |  | I | A |  |  |  | R |  |  |  | I | I | I | I | I | I
Kickoff call with AT&T UC | I | I |  |  | I | R |  |  |  |  | C |  |  | I | I | I | I | I | A
Porting Workbook provided to AT&T UC | I | I | I |  | I | I | [7 empty] | I | I | I | I | I | R
Agency provides phone and headset requirements so hardware order can be placed | I | C | I |  | I | I |  |  | C | [5 empty] | C |  | I | I | A
Agency provides call tree scripts and .wav files if applicable - requirements gathering that is documented | I | I |  |  | I | I |  |  | C | [5 empty] | C |  |  |  | A
Agency and UC PM freezes the onboarding work book pre port | [5 empty] | A | [7 empty] | I | I | I | I | I | R
UC Support PM Submits CSR Request (Customer Service Record) - verify customer's numbers | I | I |  |  | I | A | [7 empty] | I | I | I | I | I | I
UC Support Team Creates & Submits Port Request to IP Flex Port Team | I | I | I |  | I | A | [7 empty] | I | I | I | I | I | I
Port request is scrubbed & flows through ordering systems and process | I | I |  |  | I | A | [12 empty] | R
Porting Order Manager Provides FOC Date for Porting | I | I | I |  | I | A | [7 empty] | I | I | I | I | I | C
AT&T Ships Phones and hardware to agency (if applicable) | I | I | A |  | I | I | [7 empty] | I | I | I | I | I | R
Port Prep | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
UC PM provides port date & required Port info to UC NOC Team | I | I |  |  | I | A | [7 empty] | I | I | I | I | I | C
DET moves online users from online in Office 365 to the ATTUCS SFB pool. | I | I |  |  | I | [8 empty] | R | C |  |  |  | C
Agency and/or DET provides IP Addresses for analog fax gateways | I | I |  |  | I | I | [7 empty] | R | R |  |  |  | R
Agency and/or DET provides IP Addresses for any polycom phones | I | I |  |  | I | [8 empty] | I | I |  |  |  | R
Agency to provide MAC addresses for all basic and enhanced profile phones if not already included on workbook | I | I |  |  | I | [13 empty] | A
UC NOC Pre-Stage Users in Portal and IP Phone Manager and pushes most recent firmware to phone | I | I |  |  | I | A |  | R | [5 empty] | I | I |  |  |  | I
UC Team completes routing requirements | I | I |  |  | I | A |  | R | [5 empty] | I | I |  |  |  | I
UC Team configures analog fax gateways (if applicable) | I | I |  |  | I | A |  | R | [5 empty] | I | I |  |  |  | I
UC Team configures polycom phones (if applicable) | I | I |  |  | I | A |  | R | [5 empty] | I | I |  |  |  | I
UC Team creates hunt/response groups and call tree recordings (if applicable) | I | I |  |  | I | A |  | R | [5 empty] | I | I |  |  |  | C
ATT to conduct Agency web based "train the trainer" training (15 customer admin staff for each session (30 total)) | I | I |  |  | I | A |  | R | [7 empty] | I |  |  | C
Migration | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
Agency user migration/port Completion | I | I | I |  | I | A | [7 empty] | I | I | I | I | I | R
Test/Validate Port Turn-up | I | I |  |  | I | A | [7 empty] | I | I | I | I | I | R
Move to Ops | I | I |  |  | I | A |  |  |  | I |  | R | C | I | I | I | I | I | R
Close the port project | I | I |  |  | I | A | [6 empty] | R | I | I | I | I | I | R
Post Migration | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
Post Migration Support | I | I |  |  | I | I | A |  |  |  |  | R | C | C | C |  |  |  | R
Verify all tasks complete | I | I |  |  | I | A | [7 empty] | I | I |  |  |  | R
Enduser Validation & Sign off | I | I |  |  | I | [8 empty] | I | I |  |  |  | R
Agency moves into Day 2 Support | I | I | I |  | I | A | [7 empty] | I | I |  |  |  | R
Handoff from AT&T Project support to Agency/Enterprise Service Desk (ESD) support team | I | I |  |  | I | A |  | R | [5 empty] | R | R | R
Close Project | I | I | I |  | I | A | [7 empty] | R | R | R |  |  | C
Summarize Project Results and Lessons Learned | I | I | I |  | I | A | [7 empty] | R | R | R |  |  | C
Close Project Records (Update Dashboard, Agency Project Plan, Post final workbook to DET Sharepoint Site | I | I | I |  | I | A | [7 empty] | R | R | R
CPE Install Services - Optional | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
AT&T Customer Premise Installation Services - Definition (Section 3.5) - OPTION | I | I | I |  | I | A |  |  |  | C | C | [7 empty] | R
Reports | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
Weekly Reporting - Summary report of weekly ticket activity showing all tickets opened, closed and still active tickets |  |  |  |  | C | I | A |  |  |  |  | R |  | I | I | I | I | I
Monthly Performance Reporting - monthly report look at contracted infrastructure devices. UC Services Support will send out detailed reports to desinated contact person(s) | I | I | I |  | C | I | A |  |  |  |  | R |  | I | I | I | I | I
AT&T Monthly Report Metrics - if requested - relevant to service option | I | I | I |  | C | I | A |  |  |  |  | R |  | I | I | I | I | I
Strategic Reporting - Periodic Business Review - Provide business intelligence information based on the data that the UC Services Support gathers during the period under investigation. | I | I | I |  | C | I | A |  |  |  |  | R |  | I | I | I | I | I
Strategic Reporting - Performance Analysis - provide detailed information reflecting overall performance of the managed network | I | I | I |  | C | I | A |  |  |  |  | R |  | I | I | I | I | I
Web Portal Access (Ticketing Portal & Avatar) | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
Provide access to ticketing system and monitoring tools via secure Web Portal - 24x7x365 read only access |  |  |  |  | I | [6 empty] | R | A |  |  | I
A list of authorized end user contact(s) will need to be provided to the UC Services Support for access into the Web Portal. List to be provided at end user kickoff meeting. | [5 empty] | I | I |  |  |  |  | I | I |  |  | I |  |  | A
One hour Web Portal training for designated end user contacts will be scheduled thru the UC Services Support group. | [11 empty] | R | A |  |  | I
AT&T Support Services | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
Tier 1 - Tier 4 Support; MACD Support | [12 empty] | A |  |  | I
AT&T will provide remote support through AT&T's UC support center (ex: RMA, remote diagnostics & troubleshooting) | [12 empty] | A |  |  | I
AT&T Network Monitoring Center - 24x7x365 proactive monitoring - Definition (Section 3.10) | [7 empty] | A |  |  |  |  | R |  |  | I | I | I
99.99% uptime of the core data center hardware and Skype4B applications within AT&T controlled data center. Will provide monthly availability status reports. | I | I | I | I | I |  |  | A |  |  |  |  | R |  |  | I | I | I
AT&T Performance and Patch Management | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
Performance analysis of hardware, software, bandwidth utilization to identify bottlenecks and increased accuracy for capacity planning and budgeting. |  |  | I | I | I | I | [6 empty] | A | I | I | I | I | I
Patch Management for feature enhancements, bug fixes on server OS and Application software. Coordinate install with Customer (SoW) per change management and patch policies/procedures |  |  | I | I | I | I | [6 empty] | A | I | I | I | I | I | I
Best Practice monitoring and recommendations delivered via periodic business review |  |  | I | I | I | I | [6 empty] | A | I | I | I | I | I
Call Detail Records (CDR) - Ad Hoc reporting | AT&T |  |  |  |  | AT&T UC | [7 empty] | State of WI
Provides defined record retention period of CDRs per SIP Provider and timeframes to receive CDR data | I | I | I | I | I | C | C
State of Wisconsin requests CDR details for specific timeframe | I | I | I | I | I | C | C | [11 empty] | R
ATT UC provides CDR details to the State of Wisconsin | I | I | I | I | I | C | C | [6 empty] | I | I | I | I | I | I

## Names and Titles
Skype Roles and Responsibilities
Name | Role | Responsibilities
Charlene Cooley | Project Manager
Tuanna Freeman | Service Delivery Manager
JoyJit Gosh | Enhanced Skype for Business Lead
Kabena Kirkwood | Lead Architect
Steve Pitchon | Realtionship Manager
Masoud Majidi | Change Order Manager
Suman Beereddy | Sr. Incident Manager
Mohammed Fayez | Operations Manager
Tony Wineinger | Account Manager
George Kafkes | Sales Consultant
Mike Reckley | Sales Executive
Mark Beranek | Sales Consultant
Jim Holder | Sr. Inside Account Rep
Name | Role | Responsibilities
Dan Foelker | Lead Technical Architect
Matt Michel | Program Manager
Gurpeet Singh | Project Manager
Ron Garske | Telecom contract administrator
David Mastick | DOA Telecom Manager
Connie Bandt | Section Chief- Telecom Admin
Agency LCON | Agency Telecom Managers

## Definitions
R | Responsible - Assigned to complete the task or deliverable
A | Accountable - Has final decision-making authority and accountability for completion. One per task.
C | Consulted - An advisor, stakeholder, or SME who is consulted before a decision or action
I | Informed - Must be informed after a decision or action
AT&T Core Data Center Service Implementation (Section 3.4)
Examine and acquire SoW provided Microsoft S4B license for appropriate feature requirements for the UC Skype Profile. Enterprise Voice requires Microsoft Plus CAL or E5
Configure AT&T provided core hardware servers
Load core server OS and virtual applications software
Load core Microsoft applications on AT&T provided core servers
Establish integration with SoW existing Microsoft Exchange and Active Directory applications when contracted to provide
Establish core infrastructure applications database to support Skype4B features
Implementation of client on network calling between SoW locations for voice enabled profiles
Configuration of voice features within Skype4B platform for voice enabled profiles
Integration with customer provided Exchange Unified Messaging. Exchange UM lic provided by SoW
Configure Internal IM, Presence and Audio/Video conferencing
Setup dial-in conferencing, end-users can join the audio portionsof a Skype conference using PSTN access from remote locations and Skype client from SoW existing locations
Configure Microsoft Skype for Business Clients in core databases
Configure Microsoft Skype for Business Front End Servers
Configure Microsoft Skype for Business Edge Servers
Configure Microsoft Office Web Application servers
Configure Domain Controllers
Setup monitoring database
Configure Reverse Proxy
Configure Firewalls
Configure switch and Load Balancer (ATT still using DET's LB)
AT&T data center cross connects for MPLS circuits and Internet access circuits
ATT to provide network access to ATT Data Center
Terminate SIP trunks to support PSTN access
AT&T Customer Premise Installation Services (Section 3.5)
Provide customer power and environmental requirements for AT&T CPE in advance of installation
Confirm with customer that any site readiness tasks have been completed and the required circuits are provisioned and operational
Verify network configuration with customer SPOC prior to on-site installation
Unpack, inventory and inspect AT&T CPE at customer installation site
Install, rack mount and connect AT&T CPE into Customer's existing racks fro gateways and on customers desks for IP Phones. Customer must ensure appropriate AT&T CPE racks are located at agreed upon demarc points
Connect AT&T CPE to Customer provided LAN switch ports via customer provided Cat 5 or better patch cables
Provide remote technical support for AT&T on-site engineer during installation, migration, cutover and implementation testing
Troubleshoot and replace hardware failures of new AT&T CPE ("out of box failure") relating to installation/upgrade of AT&T CPE
AT&T Test and Turn-up - (Section 3.6) After installation, AT&T will manage the following functions applicable to each Site and test based on the UC Skype Profile selected
Test Dial Plan for UC Skype Basic and Enhanced profiles only
Test call transfer features for UC Skype Basic and Enhanced profiles only
Test Automated Attendant functionality and prompts as applicable for UC Skype Basic and Enhanced profiles only
Test voice mail access and retrieval for UC Skype Basic and Enhanced profiles only
Test Music on Hold as applicable for UC Skype Basic and Enhanced profiles only
Test IM and Presence for UC Skype and Enhanced Profiles only
Test conferencing for UC Enhanced Profiles only
Test AD integration
AT&T Training (Section 3.7)
Provide two web based trainings for up to 15 customer admin staff for each session (30 total)
Web Portal Access (Ticketing Portal & Avatar)
Provide access to ticketing system and monitoring tools via secure Web Portal - 24x7x365 read only access
Can view open and closed tickets
Open new tickets
Change Customer contacts and information
Network Performace Information
Device and Application Performance Information
AT&T Monthly Report Metrics (Section 3.9.B) - metrics may include:
Service Level Report
Total Incident Report
Open Incidents
Average FCRR (time to resolve)
Total Tier 2 incidents resolved
Total incidents escalated to Tier 3 or 4
Total incidents requiring AT&T CPE replacement support
AT&T Network Monitoring Center - 24x7x365 proactive monitoring Section 3.10
Server health monitoring - CPU, memory usage, power, fans, etc.
Network Call Quality monitoring , SIP Trunk, SBC and IP Phone Sets
WAN/LAN error monitoring for AT&T data center equipment
PSTN Connnections status monitoring (up/dn) for SIP trunk terminated at AT&T data center
PSTN call quality score minimum of 4.0 between SIP Trunk and AT&T data center
99.99% uptime of the core data center hardware and Skype4B applications within AT&T controlled data center. Will provide monthly availability status reports.
24/7 Fault, Event Log and Trap monitoring. Management and alerting with problem identification and triage
Customer Responsibilities (Section 4)
Provide a data network that meets VoIP traffic requirements for voice, video and data traffic demand as listed in detail in section 4.1 and summarized below
Packet loss not to exceed 1%
WAN links not to exceed 70% utilization during any period
Ethernet Network 10Mb minimum, 100Mb recommended
Cat 5 cabling infrastructure minimum
Separate Voice VLANs
Provide appropriate Skype4B licenses for enhanced and Basic profiles
Provide AD and Exchange license and servers
Provide WAN connectivity from Customer data center to end-user sites
Provide WAN connectivity from existing MPLS network to AT&T provided access to the AT&T data center
Provide internet access at customer sites
Assign a SPOC as the primary interface for the AT&T PM during engagement duration
Provide business requirements beyond Onboarding workbook to AT&T PM including gateways, pphones, dial plan, route plan, call flows, station configurations, hunt/response groups, Contact Center agents as well as IP and submet mask addressing
Provide reasonable access to AT&T along with office space as needed
Have appropriate SME and quantity of Customer personnel on-site during CPE Installs, TTU and migrations/porting events
Provide VoIP capable PC's, laptops, desk phones and/or mobile devices. AT&T not responsible for troubleshooting end-user devices, desks, chairs, printers, copiers for onsiite use.
Provide AT&T PM with local site contact name and contact information for primary and backup Agency contact(s).
Receive and secure all AT&T CPE at each site prior to on-site resource arrival. Lost items of AT&T CPE, return visits and time beyond 1 hour to locate shipments not caused by AT&T may incur additional charges
Reports (Page 24)
Weekly Reporting - Summary report of weekly ticket activity showing all tickets opened, closed and still active tickets
Monthly Performance Reporting - monthly report look at contracted infrastructure devices. UC Services Support will send out detailed reports to desinated contact person(s)
Report to include:
Network , device uptime and availability
Fault History
Trouble tickets, applicable support severity level and actual service level response time
MACD's used
Professional Services hours used
Configuration changes during the month
Strategic Reporting
Periodic Business Review - Provide business intelligence information based on the data that the UC Services Support gathers during the period under investigation.
Information to reflect CPE network trends observed, capacity planning, resource utilization trends, ticketing trends, compliance issues, best practice standards, security concerns and business continuity planning
Report goals: Characterize the existing managed environment Make specific recommendations for improvement Provide budgetary information to implement the recommendations
Recommendations will be classified as: Immediate Impact - immediate impact on performance across the managed network High Impact - provide performance improvement recommendations as well as increasing network management efficiencies Strategic Recommendations - ensuring network scalability for future business requirements and provide that end users will be able to proactively monitor and manage network performance thru the use of the UC Services Support
Performance Analysis - provide detailed information reflecting overall performance of the managed network showing bottlenecks, high utilization areas, under-utilization areas, dropped packets, unusually high error rates and lower than normal devide uptime.